## Sheet1
EJALAS TESTING REPORT
| Project Name | EJALAS | main_url | https://demo.ejalas.com
| Module Name | Login
| Reference Document | N/A
| Created By | Sandip Gyawali |  | Low Priority/Severity
| Date of Creation | 45320 |  | Medium Priority/Severity
| Date of Review | 45320 |  | High Prority/Severity
Test Case ID | Preconditions | Test Steps | Input Data | Expected Results | Actual Results | Test Environment | Execution Status | Bug Severity | Bug Priority | Attachments | Notes
1 | Must Login | 1. navigate to the page main_url/login 2. login to the page with provided username and password 3. checks the url endpoint to be on /admin/dashboard after success ful login. | Login information that includes username and password | navigates to the specified url /admin/admin | same as expected result | 1. NodeJs | Pass | Low | Low |  | This message is poped in the terminal when executing the test case as follows: [5620:5176:0109/141404.242:ERROR:page_load_metrics_update_dispatcher.cc(179)] Invalid first_paint 2.409 s for first_image_paint 2.311 s
2 | Must Login | 1. navigate to the page main_url/login 2. login to the page with the invalid credentials 3. checks if the error message has occurred with message such as invalid credentials. | Login information that includes incorrect username and password | To contain the error message with some statement | Error element with warning message | 1. NodeJs | Pass | High | High |  | This message is poped in the terminal when executing the test case as: [0109/150341.602:INFO:CONSOLE(6)] "Uncaught Error: Bootstrap's JavaScript requires jQuery", source: https://demo.ejalas.com/front/js/bootstrap.min.js
103 | Must Login | 1. navigate to the page main_url/login 2. login to the page with the valid credentials 3. after successful login navigate to the endpoint /admin/ward-wise-pratiwedan 4. click the download event button, downloads the excel file 5. check the downloaded file in the accordance downloaded path | Login inforomatiion with username and password, | Must contain the file that was downloaded | contianed the downloaded excel file in the local file structure with actual info | 1.Node Js | Pass | Low | Low |  | null
201 | Must Login | 1. navigate to the page main-url/login 2. login to the page with valid credentials 3. navigate to the endpoint /admin/role 4. enter the name of role and submit 5. check if the role has been added to the table list, as the last table element. 6. validate the rolename if matched with the given role_name that we provide. | Login informatiion with username and password, | Entered user_role name must be added to the table list | Role_name added to the list | 1.Node Js | Pass | Medium | High |  | null
202 | Must Login | 1. same as the above step no 1,2,3 of the test_id 201, 4. take one list and navigate to the edit event on that instance table list 5. edit the previous role_name with the desired new name 6. submit the new role_name 7. check the table list if the role is updated in the ui 8.validate the new updated role_name | Login information with username and password | Edited role_name must be updated in the list | Role_name updated successfully | 1.Node Js | Pass | Low | Medium |  | null
305 | Must Login | 1. navigate to the main_url/login and login with given credentials 2. navigate to the endpoint /admin/court 3. input the committie_name, prades, district and committee_type 4. submit the given information 5. check the table_list if the given info is added or not 6. validate the info with the updated list section with comittee_name, district and so on. | Login information with username and password | Addtion of committee info to the provided list | Committee info added to the list successfully | 1.Node Js | Pass | Low | Medium |  | null
306 | Must Login | 1. navigate to the main_url/login and login with given credentials 2. navigate to endpoint /admin/court 3. edit the given committee info of test_id 305 4. submit the given updated/edited information 5. check the table list if it has been updated with the information that we changed. 6.validate the list info with the edited info like comittee_name, district and so on | Login information with username and password | Modification of committee info of the provided list | Committee info edited list successfully | 1.Node Js | Pass | Low | Medium |  | null
350 | Must Login | 1. navigate to the main_url page 2. check the image if rendered/loaded to the page or not using inner width and height. 3.validate the width and height not to be 0. 4. marquee effect test that displays the content in the slide format 5. validate if the content inside the marquee is present or not | Login information with username and password | Need image not to be broken and marquee tool working on display | resulted same as the expected_results | 1.Node Js | Pass | Low | Low |  | In some page the marquee slide is not working as expected
401 | Must Login | 1. navigate to the main_url/login and perform successful login 2. navigate to the /department endpoint 3. add input department_name and submit the info 4. check the table list if it contains the latest department_name that we added 5. validate the info from the table with the given department_name that we input, must contain inside the table list after updating table | Login information with username and password | Must contain new department name after addtion in the table list | result same as the expected_results | 1.Node Js | Pass | Medium | Medium |  | null
402 | Must Login | 1. navigate to the main_url/login and perfom successful login 2. choose the department_name that we want to change 3. navgate with the edit icon event to perform the desirable changes 4. edit the input field and perform submit action 5. validate if the given department_name has been updated accordingly or not | Login information with username and password | Need to change the department_name with the latest department_name | result same as the expected_results | 1.Node Js | Pass | Medium | Medium |  | null
451 | Must Login | 1. navigate to the main_url/login and perform successful login which navigates to the /admin section with dashboard 2. checks for the label such as number of cases, successful cases count and 2 other so on. 3. validates if those info are correctly displayed. | Login information with username and password | should display the info in the 4 different label | result same as the expected_results | 1.Node Js | Pass | High | High |  | null
452 | Must Login | 1. navigate to the main_url/login and perform successful login 2. check if the chart label is shown in the dashboard page 3. validates the chart if displayed or not | Login information with username and password | should display the chart in the dashboard | result same as the expected_results | 1.Node Js | Pass | High | High |  | null
501 | Must Login | 1. navigate to the main_url/login and perform successful login 2. now navigate to the endpoint /admin/melmilapkarta-darta 3. target which table data that we want to validate and invalidate 4. navigate to the eye button beside the table data which navigates to the page that contains the detail of the concialiator 5. based on the specific condition validate or invalidate the the given concialator case 6. then validate the given the given concialtor data result based on valid and invalid option | Login information with username and password | show validate and invalidate the given concilaiator case | result same as the expected_results | 1.Node Js | Pass | High | High |  | null
551 | Must Login | 1. navigate to the main_url/login and perform successful login 2. navigate further to the /admin/complaint-type 3. input the complaint that you want to add as an issue 4, submits the input and check if the complaint has been added to the list. 5.validates the given complaint based on the addition of new table list data | Login information with username and password | should accept the complaint and table list must be updated with the input complaint | successful addition of complaint | 1.Node Js | Pass | Medium | Medium |  | null
552 | Must Login | 1. navigate to the main_url/login and perform successful login 2.navigate further to the admin/complaint-type 3. select the edit btn to update the complaint that was registered 4. input the changes that is to be made in the input label 5. submit the complaint and check in the table list has that selected section been updated? 6. validate the given result based on the selected section change. | Login information with username and password | should update the complaint with previous complaint registered | successful updation of complaint | 1.Node Js | Pass | Medium | Medium